## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Program 2025 - <Data Analytics> Project Schedule
|  | PROJECT START DATE | 2025-06-25
|  | Display Week Sr No | 1 | [10 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | time axis 2025-06-23 to 2025-08-24
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2025-06-23 to 2025-08-24
1 | Pre-IP | [5 empty] | 2025-06-25 | 2025-06-29 | 2025-06-29 | 12
1.1 |  | Understanding the data | Load and Inspect the Raw File | Inspect Excel layout, identify key sheets |  |  | 2025-06-25 | 2025-06-26 | 2025-06-26 | 3 | Completed | 100 | Initial familiarization
1.1.1 |  |  | Profile Columns | Check column types, datatypes | 1.1 |  | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2 | Completed | 100 | Initial familiarization
1.1.2 |  |  | Check for Null/Missing Values | Conditional Formatting |  |  | 2025-06-27 | 2025-06-27 | 2025-06-27 | 1.5 | Completed | 100 | Too many null values in columns like "Where did you know this event from"
1.1.3 |  |  | Check for duplicates | Conditional Formatting |  |  | 2025-06-28 | 2025-06-28 | 2025-06-28 | 1 | Completed | 100 | Decent amount of Duplicates in this data
1.1.4 |  |  | Understand data spread | Conditional Formatting | 1.1,1.1.1,1.1.2,1.1.3 |  | 2025-06-28 | 2025-06-29 | 2025-06-29 | 4 | Completed | 100 | Many conflicting rows, same students have entered different details in their entries for unique events
2 | Data Preparation & Integrity | [5 empty] | 2025-06-30 | 2025-07-06 | 2025-07-07 | 30
2.1 |  | Data Cleaning & Integrity | Drop Exact Duplicates | Learn Pandas and use Pandas function like df.drop duplicates() | 1.1.4 |  | 2025-06-30 | 2025-07-01 | 2025-07-02 | 12 | Completed | 100 | Learnt Pandas and its function
2.1.1 |  |  | Resolve Conflicting Values | Apply mode for Categorical values and median for numeric | 2.1 |  | 2025-07-02 | 2025-07-03 | 2025-07-04 | 5 | Completed | 100 | It was so frustating to resolve these rows , took many tries
2.1.2 |  |  | Flag Untrusted Records | Mark CGPA‑range >1 or multiple cities as NO in "Is Trusted" | 2.1.1 |  | 2025-07-03 | 2025-07-04 | 2025-07-05 | 5 | Completed | 100 | For Integrity Check
2.2 |  | Data Transformation | Build Consistent Student Profile | Group by Email ID , merge cleaned fields back | 2.1 |  | 2025-07-04 | 2026-07-05 | 2025-07-06 | 5 | Completed | 100 | Reference Profile and then we merge cleaned files back
2.3 |  | Data Export and Checking Data | Save Cleaned Dataset to Excel and check the cleaned data | df.to_excel("Cleaned_Data.xlsx"),checking every field for cleaned data | 2.2 |  | 2025-07-06 | 2025-07-06 | 2025-07-07 | 3 | Completed | 100 | Downloading the cleaned excel file and check the data for any inconsistency , again took many tries to get the cleaned data
3 | Analysis & Visualization | [8 empty] | 31
3.1 |  | Analysis and Visualization | Review & Clarify Questions | Read through Q1-Q18 and understand them thoroughly | 2.2 |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 3 | Completed | 100 | I did read all the question and attempted 16
3.1.2 |  |  | Load cleaned excel into tableau | load cleaned excel file in tableau and create calculated column necessary for questions | 2.2,3.1 |  | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2 | Completed | 100 | I loaded the excel file ,but real hard thing was to create required calculated columns neccesary for specific questions
3.1.1 |  |  | Workbook/Dashboard Skeleton | Sketch layout for all views (charts, filters, titles) | 3.1.2 |  | 2025-07-09 | 2025-07-10 | 2025-07-09 | 2 | Completed | 100 | made the layout and filters ready for the questions
3.1.2 |  |  | Core Charts Development and analyzing the relevant question | Solve Q1-Q18 using relevant charts or scatter plot or dashboard wherever it is necessary and analyze them | 1,2,3.1 |  | 2025-07-10 | 2025-07-11 | 2025-07-12 | 20 | Completed | 100 | It really took me a while to solve the questions ,there were many things I have to take in consideration and had to backtrack sometimes
3.2 |  | Report writing | Wrote the project document and project report |  | 1,2,3 |  | 2025-07-12 | 2025-07-12 | 2025-07-13 | 4 | Completed | 100 | Yep,Documentation
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you