## Sheet1
Date | Activity | Description | Tools Used | Status | Time Spent (hrs) | Comments
25‑Jun‑25 | Project Kickoff | Reviewed objectives, scoped questions Q1–Q18 | Excel, Industry Academia Website | Completed | according to project schedule | Confirmed deliverables and timeline
26‑Jun‑25 | Data Ingestion | Loaded raw Excel, inspected sheets, noted data issues | Excel | Completed | according to project schedule | Identified duplicates and missing values
26‑Jun‑25 | Data Profiling | Ran .info(), .describe(), value_counts(), duplicated() | Pandas | Completed | according to project schedule | Documented field types and extent of nulls
02‑Jul‑25 | Conflict Resolution Logic | Implemented mode/median rules; flagged tie/conflict cases | Pandas | Completed | according to project schedule | Created Is_Trusted flag
06‑Jul‑25 | Data Cleaning | Dropped duplicates, filled missing categoricals, imputed nums | Pandas | Completed | according to project schedule | Produced cleaned dataset for export
07‑Jul‑25 | Export for Visualization | Exported cleaned data to Excel for Tableau import | Pandas, Excel | Completed | according to project schedule | Saved as Cleaned_Data.xlsx
09‑Jul‑25 | Tableau Dashboard Setup | Connected data source, built initial Q1–Q5 views | Tableau | Completed | according to project schedule | Created bar, scatter, and map charts
10‑Jul‑25 | Advanced Tableau Visuals | Added Q6–Q9 trendlines and filters | Tableau | Completed | according to project schedule | Incorporated Is_Trusted filter
11‑Jul‑25 | Moderate Questions Charts | Developed Q10–Q18 dashboards (city, salary, DS events, leadership) | Tableau | Completed | according to project schedule | Used COUNTD, SPLIT, LOD calculations
11‑Jul‑25 | Final Visual Polishing | Applied consistent color schemes, labels, tooltips | Tableau | Completed | according to project schedule | Ensured readability and interactivity
12‑Jul‑25 | Report Writing: Methods & Findings | Drafted methodology, findings, and conclusion sections | Word, Excel | Completed | according to project schedule | Embedded screenshots and captions