## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analytics
INTERN NAME: | Shivohum Pandita
PROJECT NAME: | ABSENCE OF INSIGHTS FOR THE RELATIONSHIP BETWEEN STUDENT'S ECONOMIC BACKGROUND, ACADEMIC PERFORMANCE, COMPETENCE & EXPECTED SALARY.
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2025-06-28
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | ABSENCE OF INSIGHTS FOR THE RELATIONSHIP BETWEEN STUDENT'S ECONOMIC BACKGROUND, ACADEMIC PERFORMANCE, COMPETENCE & EXPECTED SALARY.
PROJECT ID | GPI 2025 <Data Analysis>
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2025-06-27 | Found duplicate students with mismatched CGPA and city | Data Cleaning | Yes | Integrity Check | Applied conflict resolution rules and flagged conflicts |  | Closed | Happened during data merging
2 | 2025-06-28 | Building the project schedule template | Project Planning | Yes | Allocate time to draft the schedule template before data work | Created and reviewed the week‑by‑week Excel schedule |  | Closed | Used the IAC template directly
3 | 2025-06-29 | Delay in visualization due to underestimated cleaning time | Project Planning | No |  | Had to adjust my time for documentation |  | Closed | Affected the timeline
4 | 2025-07-02 | No initial documentation during conflict resolution | Documentation | No | Maintain documents from Day 1 | started maintaining documents alongside the tasks |  | Closed | Improved efficiency,clarity
5 | 2025-07-09 | Multi-response fields causing import issues in Tableau | Data Formatting | No |  | Used Tableau to split separated entries into lists |  | Closed | Happened when I loaded data into Tableau
6 | 2025-07-11 | Late consideration of the Designation field and bias that it is a student data led to dashboard redesign | Data Understanding | Yes | Understand each field thoroughly no matter how insignificant it seems | Had to put the filter for Designation Student |  | Closed | Affected data analysis